## Concrete Work
Task | Duration | Dependency | Cluster | Material | 4DRelevant | EBKP
Survey and layout for slab and wall positions | 2 days | None | General | To be defined | Yes | -
Formwork placement for columns and beams | 3 days | Survey and layout | Structural | Plywood, Steel | No | -
Formwork placement for walls | 3 days | Formwork placement for columns and beams | Structural | Plywood, Steel | No | -
Formwork placement for slabs | 4 days | Formwork placement for walls | Structural | Plywood, Steel | No | -
Reinforcement bar cutting and bending | 2 days | Formwork placement for slabs | Structural | Rebar Steel | No | -
Placement of reinforcement bars in columns and walls | 3 days | Reinforcement bar cutting and bending | Structural | Rebar Steel | No | -
Placement of reinforcement bars in slabs | 2 days | Placement of reinforcement bars in columns and walls | Structural | Rebar Steel | No | -
Concrete pouring for columns | 2 days | Placement of reinforcement bars in columns and walls | Concrete | Concrete | Yes | C03.01: Aussenstütze
Concrete pouring for walls | 2 days | Concrete pouring for columns | Concrete | Concrete | Yes | C02.01: Aussenwandkonstruktion
Concrete pouring for slabs | 3 days | Concrete pouring for walls | Concrete | Concrete | Yes | C01.03: Bodenplatte
Initial surface leveling | 1 day | Concrete pouring for slabs | General | To be defined | No | C05.01: Durchbruch, Schlitz zu Konstruktion
Concrete curing | 7 days | Initial surface leveling | Concrete | Concrete | No | C05.01: Durchbruch, Schlitz zu Konstruktion
Removal of formwork | 2 days | Concrete curing | Structural | Plywood, Steel | No | -
Surface cleaning and preparation | 3 days | Removal of formwork | General | To be defined | No | C05.01: Durchbruch, Schlitz zu Konstruktion

## Electrical Work
Task | Duration | Dependency | Cluster | Material | 4DRelevant | EBKP
Demarcation of cable tray path on the slab | 2 Days | None | General | To be defined | No | D01.04: Installation Starkstrom
Cable tray support bracket/Thread bar installation | 1 week | None | General | To be defined | Yes | D01.04: Installation Starkstrom
Resolve in conflict issues with any other service installation | 3 days | other mechanical services | General | To be defined | Yes | -
Cable tray installation | 4 weeks | None | General | To be defined | Yes | D01.04: Installation Starkstrom
Demarcation of Surface slab/wall conduit path | 1 week | None | General | To be defined | No | D01.04: Installation Starkstrom
Marking of Wall back box locations for socket outlets and switches | 2 weeks | None | General | To be defined | Yes | D01.04: Installation Starkstrom
Wall chasing for conduit installation from cable tray to wall boxes | 3 weeks | None | General | To be defined | Yes | D01.04: Installation Starkstrom
Wall back boxes/soffit junction boxes installation | 2 weeks | None | General | To be defined | Yes | D01.04: Installation Starkstrom
Conduit installation | 3 weeks | None | General | To be defined | Yes | D01.04: Installation Starkstrom
Main feeder cable laying from MSB to Floor DB | 3 days | None | General | To be defined | No | D01.04: Installation Starkstrom
Sub feeder cable laying from Floor DB to Sub DBs | 4 days | None | General | To be defined | No | D01.04: Installation Starkstrom
Final circuit wiring for mechanical equipment | 1 week | None | General | Copper Wire | No | D01.06: Verbraucher Starkstrom: Elektrogeräte
Final sub circuit wiring for lighting | 3 weeks | None | General | Copper Wire | No | D01.05: Verbraucher Starkstrom: Leuchten
Final sub circuit wiring for power outlets | 3 weeks | None | General | Copper Wire | No | D01.04: Installation Starkstrom
Cable tray and metal conduit equipotential earth wire installation | 3 days | None | General | To be defined | Yes | D01.04: Installation Starkstrom
Light fixture Installation and termination | 3 weeks | Ceiling installation | General | To be defined | Yes | D01.05: Verbraucher Starkstrom: Leuchten
Power outlet Installation and termination | 2 weeks | Wall finishing | General | To be defined | Yes | D01.04: Installation Starkstrom
Wall switches Installation and termination | 3 weeks | Wall finishing | General | To be defined | Yes | D01.04: Installation Starkstrom
Mechanical equipment cable termination | 1 week | Mechanical equipment installation | General | To be defined | No | D01.06: Verbraucher Starkstrom: Elektrogeräte
Sub power DB installation | 5 days | None | General | To be defined | Yes | D01.04: Installation Starkstrom
Wall cable trucking/ladder installation for DBs | 1 week | None | General | To be defined | Yes | D01.04: Installation Starkstrom
Power DB main feeder cable and sub feeder cable termination | 2 days | None | General | To be defined | No | D01.04: Installation Starkstrom
Final sub circuit termination in DBs | 2 weeks | None | General | To be defined | No | D01.04: Installation Starkstrom
Testing and Commissioning | 3 weeks | None | General | To be defined | No | W05.01: Inbetriebnahme Bauwerk

## Sanitary Work
Task | Duration | Dependency | Cluster | Material | 4DRelevant | EBKP
Marking and layout of plumbing routes | 2 days | Concrete curing | General | To be defined | Yes | D08.06: Wasser: Installationselement
Excavation for drainage pipes | 2 days | Marking and layout of plumbing routes | Sanitary | PVC, Steel | No | D09.04: Abwassersammlung
Laying of drainage pipes | 5 days | Excavation for drainage pipes | Sanitary | PVC, Steel | No | D09.04: Abwassersammlung
Sealing and joint testing of drainage system | 2 days | Laying of drainage pipes | General | To be defined | No | D09.04: Abwassersammlung
Installation of cold water supply pipes | 5 days | Marking and layout of plumbing routes | Sanitary | PVC, Steel | Yes | D08.04: Wasserverteilung
Installation of hot water supply pipes | 4 days | Installation of cold water supply pipes | Sanitary | PVC, Steel | Yes | D08.04: Wasserverteilung
Insulation of hot water pipes | 3 days | Installation of hot water supply pipes | Sanitary | PVC, Steel | No | D08.04: Wasserverteilung
Installation of toilet fixtures | 3 days | Sealing and joint testing of drainage system | General | To be defined | Yes | D08.06: Wasser: Installationselement
Installation of sinks and basins | 3 days | Sealing and joint testing of drainage system | General | To be defined | Yes | D08.06: Wasser: Installationselement
Installation of shower fixtures | 2 days | Sealing and joint testing of drainage system | General | To be defined | Yes | D08.06: Wasser: Installationselement
Pressure testing of water supply pipes | 1 day | Installation of toilet fixtures | Sanitary | PVC, Steel | No | D08.04: Wasserverteilung
Flow testing for drainage system | 1 day | Pressure testing of water supply pipes | General | To be defined | No | D09.04: Abwassersammlung

## Ventilation
Task | Duration | Dependency | Cluster | Material | EBKP
Marking of ventilation duct paths | 2 days |  | Mechanical | Sheet Metal | B01.02: Bestandsaufnahme
Installation of duct supports | 3 days | Marking and layout for duct routes | Mechanical | Sheet Metal | D07.04: Luftverteilung
Installation of ventilation ducts | 7 days | Installation of duct supports | Mechanical | Sheet Metal | D07.04: Luftverteilung
Fixing air grilles and diffusers | 3 days | Laying of ductwork | Mechanical |  | D07.05: Luftabgabe
Ventilation system testing and commissioning | 2 days | Installation of HVAC units (compressors, blowers) | General | To be defined | W05.01: Inbetriebnahme Bauwerk

## Heating-Cooling
Task | Duration | Dependency | Cluster | Material | 4DRelevant | EBKP
Marking and layout for duct routes | 2 days |  | Mechanical | Sheet Metal | Yes | D05.06: Wärmebezug: Investitionsanteil
Installation of duct supports | 3 days | Marking and layout for duct routes | Mechanical | Sheet Metal | Yes | D05.06: Wärmebezug: Investitionsanteil
Laying of ductwork | 7 days | Installation of duct supports | Mechanical | Sheet Metal | No | D05.06: Wärmebezug: Investitionsanteil
Installation of HVAC units (compressors, blowers) | 3 days | Laying of ductwork | Mechanical |  | Yes | D05.06: Wärmebezug: Investitionsanteil
Fixing air diffusers and grilles | 2 days | Installation of HVAC units (compressors, blowers) | General | To be defined | Yes | D05.06: Wärmebezug: Investitionsanteil
Installation of refrigerant piping | 3 days | Fixing air diffusers and grilles | General | To be defined | Yes | D06.04: Kälteverteilung
Insulation of refrigerant piping | 2 days | Installation of refrigerant piping | General | To be defined | No | D06.04: Kälteverteilung
Water piping for heating/cooling units | 4 days | Fixing air diffusers and grilles | General | To be defined | No | D05.04: Wärmeverteilung
Cabling for HVAC units | 2 days | Installation of HVAC units (compressors, blowers) | Mechanical | Copper Wire | No | D05.06: Wärmebezug: Investitionsanteil
Installation of control panels and thermostats | 2 days | Cabling for HVAC units | General | To be defined | Yes | D05.06: Wärmebezug: Investitionsanteil
Leak testing for refrigerant piping | 1 day | Insulation of refrigerant piping | General | To be defined | No | D06.04: Kälteverteilung
System testing and commissioning | 2 days | Leak testing for refrigerant piping | General | To be defined | No | D05.06: Wärmebezug: Investitionsanteil

## Sprinkler Work
Task | Duration | Dependency | Cluster | Material | 4DRelevant | EBKP
Marking of sprinkler pipeline routes | 1 day | Concrete curing | Sanitary | PVC, Steel | Yes | D08.04: Wasserverteilung
Installation of supports for sprinkler pipes | 2 days | Marking of sprinkler pipeline routes | Sanitary | PVC, Steel | Yes | D08.04: Wasserverteilung
Laying of sprinkler pipes | 4 days | Installation of supports for sprinkler pipes | Sanitary | PVC, Steel | No | D08.04: Wasserverteilung
Installation of pipe joints and valves | 3 days | Laying of sprinkler pipes | Sanitary | PVC, Steel | Yes | D08.04: Wasserverteilung
Fixing of sprinkler heads in walls and ceilings | 3 days | Installation of pipe joints and valves | Fire Safety | PVC, Steel | Yes | D04.03: Nasslöschanlage
Pressure testing of sprinkler system | 1 day | Fixing of sprinkler heads in walls and ceilings | Fire Safety | PVC, Steel | No | D04.03: Nasslöschanlage
System commissioning | 1 day | Pressure testing of sprinkler system | General | To be defined | No | W05.01: Inbetriebnahme Bauwerk

## Building Automation
Task | Duration | Dependency | Cluster | Material | 4DRelevant | EBKP
Installation of main control panels | 3 days | None | General | To be defined | Yes | D02.07: Systemintegration
Placement of temperature sensors | 2 days | Installation of main control panels | Automation | Electronics | No | D02.03: Feldebene
Placement of motion sensors | 2 days | Placement of temperature sensors | Automation | Electronics | No | D02.03: Feldebene
Installation of lighting control sensors | 2 days | Placement of motion sensors | Automation | Electronics | Yes | D02.03: Feldebene
Fixing actuators for HVAC systems | 3 days | Placement of motion sensors | Mechanical | To be defined | Yes | D02.07: Systemintegration
Fixing actuators for shading systems | 2 days | Fixing actuators for HVAC systems | General | To be defined | Yes | D02.07: Systemintegration
Cabling for control panels to sensors and actuators | 7 days | Fixing actuators for HVAC systems | Automation | Electronics | No | D02.03: Feldebene
Integration of lighting, HVAC, and security systems | 3 days | Cabling for control panels to sensors and actuators | Mechanical | To be defined | No | D02.05: Automationsnetzwerk
System testing for automation controls | 2 days | Integration of lighting, HVAC, and security systems | Automation | To be defined | No | D02.07: Systemintegration
Final commissioning | 1 day | System testing for automation controls | General | To be defined | No | D02.07: Systemintegration